## Sheet1
Issue | State | Description | Comment | ETA | Status | State
1 | Monitor | Date Format Confusion | Tool Tip date format change to DD-MON-YY. Provided option to set the desired ofrmat in configuration menu. | 2026-07-17 |  | Resolved
Done
2 | Monitor | Red carrot due date on Gantt Planner | Will Restore flag | 2026-07-17 | Done | Resolved
3 | Monitor | Preview WO popup truncation | a) Dynamically adjust pop-up size | a) 17 July | Done | Resolved
|  |  | b) Click outside pop-up to close | b) Next Release
4 | More info | Toolbar ellipsis displays overlapping fields | ?? |  | November Release | Pending
5 | Monitor | Output too large max 4000 records | Limit results to 4000. Update config menu to set own limit w/max of 4000 | Next Release | Next Release | Pending
6 | Resolved | Future PM meaning | Hourglass icon. Gantt w/ diff color. They are future duplicate WOs not yet released. Can be overdue or placeholder for future work. | - - | - | Resolved
7 | Resolved | Pop-up WO details off screen | By design to avoid masking WO Grid details | - - | By Design | Resolved
8 | Resolved | Hourglass v.s. Wrench icons | Wrench = actual WO. | - - | - | Resolved
Hourglass = Future event.
Number above hourglass = future sequence for that PM Schedule.
Tooltip on hover for details.
9 | Resolved | Global Search | Obsolete and will be removed | 2026-07-17 |  | Resolved
10 | More info | Excel Export | Unable to reproduce. Want to validate in our Train environment. |  | Pending | Resolved
11 | Monitor | WO Grid Sorting | Will fix caret alignment | 2026-07-21 |  | Pending
12 | Monitor | WO Grid Sched Start Date, EVT_TARGET, Earliest Completion Date | a) Will rename fields. | ?? | Next Release | Pending
|  |  | b) Use Boiler plate names | Future release
13 | Monitor | Date Filter Before/After and < vs <= | Will fix functionality | 2026-07-21 | Done | Resolved
14 | Resolved | Column Filters = Contains and case sensitivity | Yes: Contains, not case-sensitive | - - | - | Resolved
15 | Resolved | Multiple filter use AND logic | Yes: multiple columns use “AND” operator. If OR is needed use a Dataspy | - - | - | Resolved
16 | Resolved | Does Gantt bar affect Duration? | No | - - | - | Resolved
17 | Monitor | Dataspy editor uses database column names | Update to business names | Next release | Pending | Pending
18 | Monitor | Popup carries over to other EAM screens | Not consistent behavior. Will fix | Future release |  | Resolved
19 | Monitor | Modify holidays | Will provide Admins with access | Next release |  | Pending
20 | Monitor | Screen Cache | Not available. But will create a Save Filters button | November release |  | Pending
Agreed to provide save filter option
21 | Resolved | WO Details adjust fields displayed | No way to change | - - | Pending | Resolved
22 | Resolved | Day view Gantt Column numbers | Number is estimated hours for that day for WO shown | - - | - | Resolved
23 | More info | Clicking date in column title shows Day View for prior day | Not currently reproduceable | Not an Issue |  | More info
24 | Monitor | Review Pending Changes days counter off by 1 | Will fix | 2026-07-17 |  | Resolved
25 | Monitor | Quick Update to dates not reflected in Grid/Details | Will fix | Next release |  | Pending
Workaround: Click Refresh
26 | New | Past WO not showing w/ past From date |  | Not an Issue |  | Resolved
27 | New | Configuration changes not saved across sessions |  |  |  | Pending
28 | New | Future Work iterations counter limit |  |  |  | Resolved
29 | New | WO Daily List / Hours not accurate |  | Not an Issue | Done | More info
30 | New | Toolbar Organization filter only matches on ORG description |  |  | Done | Resolved